Document 4: Project Roadmap, Resource Allocation & Collaboration Agreement

llm-society-sim • Version 1.0 • Internal Project Management, 8-Week Timeline, Task Matrix & Budget Strategy

| Project Title: | Diversity as a Defense Against Misinformation in LLM Societies |
| --- | --- |
| Internal Lead & Theorist: | Co-Researcher A (Lead Author & Project Initiator) |
| Engineering & Compute Lead: | Co-Researcher B (Systems, API & Modal Lead) |
| Target Outcomes: | ArXiv Preprint, Workshop Submission (NeurIPS/ICLR/ICML), Open-Source Python Package |
| Application Focus: | Fall 2027 Master's Program Profile Enhancement (CMU, Stanford, ETH Zurich, UC Berkeley, UIUC) |

1. Collaboration Charter & Master's Portfolio Objectives

This document serves as the operational contract and roadmap between Co-Researcher A and Co-Researcher B. The primary objective is to execute a high-impact, scientifically sound research study that results in a peer-reviewed publication or workshop acceptance, strengthening both researchers' Fall 2027 graduate application portfolios.

Strategic Positioning: Admissions committees at top-tier CS and AI programs evaluate applicants based on proof of original research capability, methodological rigor, clean software engineering, and collaborative leadership rather than compute budget scale. Co-authoring a polished, open-source research artifact fulfills all these criteria.

Key Collaboration Principles:
1. Equal co-authorship contribution toward the ArXiv paper and workshop submission.
2. Shared ownership of the open-source llm-society-sim repository.
3. Transparent tracking of cloud credits ($280 Modal pool) and out-of-pocket expenses ($120 cash cap).
4. Strict adherence to the 8-week completion timeline.

2. 8-Week Phased Execution Roadmap

The 8-week execution pipeline is broken down into four distinct 2-week sprints, ensuring steady progress toward paper submission:

Phase 1: Architecture & Pipeline Build (Weeks 1–2)

• Finalize repository structure (config.py, graph.py, memory.py, router.py).
• Implement async rate-limiters for Groq, Cerebras, and Google AI Studio APIs.
• Validate network topology generators (Complete, Erdos-Renyi, Watts-Strogatz).
• Milestone: Successful execution of a 20-agent dry-run across 5 rounds.

Phase 2: Matrix Execution & Probing (Weeks 3–4)

• Launch 405 simulation runs across the 15 diagnostic facts suite and 3 prompt seeds.
• Deploy Modal serverless GPU prober to compute batch token logprobs for B_i^(t).
• Collect 150 agent response samples and launch Prolific human validation tasks.
• Milestone: Complete JSON trajectory dataset generated and verified.

Phase 3: Data Analytics & Dashboard Build (Weeks 5–6)

• Run ANOVA, Kolmogorov-Smirnov, and Linear Mixed-Effects Models (LMM) in Python.
• Generate publication-ready Seaborn plot figures (TRR trajectories, BPI polarization, R0 curves).
• Construct an interactive Streamlit / D3.js web dashboard for live graph visualization.
• Milestone: Statistical significance validated (p < 0.01) and web demo deployed.

Phase 4: Paper Writing, ArXiv & Submission (Weeks 7–8)

• Write full 4–8 page research paper formatted in official NeurIPS/ICML LaTeX style.
• Incorporate mathematical formulations, literature gap table, and empirical results.
• Upload preprint to ArXiv and submit paper to targeted AI Safety / Multi-Agent workshop.
• Milestone: Official ArXiv identifier received and workshop submission confirmed.

3. Work Division & Task Ownership Matrix

To prevent ambiguity and maintain momentum, specific primary and secondary responsibilities are assigned across both co-researchers:

| Module / Research Area | Primary Lead | Secondary / Support | Key Deliverable Output |
| --- | --- | --- | --- |
| Theoretical Formulation & Hypotheses | Co-Researcher A | Co-Researcher B | Doc 1 LaTeX math equations & H1–H4 statements |
| Async API Router & Rate Limiting | Co-Researcher B | Co-Researcher A | router.py module (Groq/Cerebras/Gemini engine) |
| Network Topology & Memory Engine | Co-Researcher B | Co-Researcher A | graph.py & memory.py (NetworkX & tiktoken) |
| 15 Diagnostic Facts Curation | Co-Researcher A | Co-Researcher B | Fact taxonomy, injected prompts & verbal templates |
| Modal GPU vLLM Prober Setup | Co-Researcher B | Co-Researcher A | modal_prober.py batch logit extractor |
| Batch Simulation Execution (405 Runs) | Co-Researcher B | Co-Researcher A | Full results_trajectory.json dataset |
| Human Validation & Calibration | Co-Researcher A | Co-Researcher B | Prolific dataset & Fleiss' Kappa correlation |
| Statistical Significance Pipeline | Co-Researcher A | Co-Researcher B | ANOVA, K-S test, and Seaborn figure plots |
| Streamlit / D3.js Web Dashboard | Co-Researcher B | Co-Researcher A | Interactive live network visualization web app |
| LaTeX Paper Writing & Submission | Co-Researcher A | Co-Researcher B | ArXiv preprint PDF & Workshop submission |

4. Resource Allocation & Budget Management

The project is specifically optimized to run within a strict out-of-pocket cash limit of $120.00 while utilizing a $280.00 Modal credit pool and free-tier commercial LLM APIs.

| Resource Category | Allocated Cap | Funding Source | Usage Estimate | Status / Buffer |
| --- | --- | --- | --- | --- |
| Text Generation APIs | $0.00 | Groq, Cerebras, Gemini Free | 40,500 free API calls | Zero Cash Cost |
| Logit GPU Probing | $120.00 | Modal Credits ($280 Pool) | ~120 GPU hours on L4 | $160 Credit Buffer Remaining |
| Human Validation | $40.00 | Out-of-Pocket Cash | 150 ratings @ $0.25 | Within $120 Cash Cap |
| Workshop Registration | $80.00 | Out-of-Pocket Cash | Student Registration Rate | Within $120 Cash Cap |
| Code & Data Hosting | $0.00 | GitHub & Hugging Face | Public Repo & Dataset Space | Zero Cash Cost |
| TOTAL OUT-OF-POCKET | $120.00 | Out-of-Pocket Cash | Full 8-Week Execution | Exact Target Budget Met |

5. Publication Strategy & Target Venues

To maximize visibility and academic credibility, the research output follows a phased release strategy:

1. Primary Workshop Submission: Target AI Safety, Multi-Agent Systems, or AI Civilization workshops at top-tier AI venues such as NeurIPS, ICLR, ICML, COLM, or ACL Findings.

2. ArXiv Preprint Release: Publish the fully formatted LaTeX draft on ArXiv simultaneously with workshop submission, establishing early claim on the research topic.

3. Open-Source Software Release: Publish the complete llm-society-sim codebase on GitHub under the MIT License, formatted with clean documentation, PyPI support, and unit tests.

4. Dynamic Interactive Web Demo: Host an interactive D3.js or Streamlit web application on GitHub Pages / Streamlit Cloud allowing visitors to simulate misinformation spread in real time.

6. Risk Contingency Protocols

To ensure project completion without delays or budget overruns, pre-planned contingency protocols are established:

Risk Management & Contingency Protocols Risk 1: API Rate Limiting or Provider Downtime • Mitigation: AsyncLLMRouter automatically fails over across Groq, Cerebras, and Gemini endpoints with exponential backoff. Risk 2: Modal GPU Credit Exhaustion • Mitigation: The $280 credit pool provides a 100% safety buffer over the $120 estimated probing cost. If needed, quantization (AWQ/GGUF) reduces GPU time by 50%. Risk 3: Unexpected Statistical Non-Significance (H1/H2) • Mitigation: Negative or neutral findings will be framed as a discovery regarding model alignment convergence rather than failure, preserving paper publishability.