PROJECT BRIEFING & COLLABORATION PROPOSAL

Diversity as a Defense Against Misinformation in LLM Societies

Do architecturally diverse populations of language-model agents resist misinformation cascades better than homogeneous ones — once you control for capability?

| Field | Value |
| --- | --- |
| Prepared by | Abhijit Kumar |
| For | Divyesh, IIT KGP |
| Date | 8 August 2026 |
| Purpose | First detailed walkthrough of the project; agree scope, roles and next steps |
| Status | Design phase (Gate G1). No experimental data collected yet. |
| Repository | github.com/Abhijit89Kumar/Diversity-as-a-Defense-Against-Misinformation-in-LLM-Societies (public) |
| Target output | arXiv preprint + AI-safety / multi-agent workshop paper; open-source package |

How to read this document Sections 1–3 are the pitch: what the question is and why it is still open. Sections 4–6 are the current state — what is designed, built and already validated. Section 7 is what is hard, stated plainly. Sections 8–11 are the proposal: how we would work, who does what, and what we need from the institute. Section 11 is the agenda. If we only get through one section together, make it that one.

# 1.  The project in one page

## The question

Large language models are increasingly deployed in groups — agents that talk to each other, review each other’s work, and reach a shared answer with no human in the loop. When one agent in such a group is wrong, or has been deliberately fed a falsehood, that error can spread. We want to know what makes a population resistant.

Specifically: if the agents in a group are architecturally different from one another — different model families, trained by different labs on different data — do they resist an injected falsehood better than a group of identical agents of the same overall capability?

## Why it is not already answered

Four studies published in 2025–26 report effects of model heterogeneity in multi-agent systems, and they disagree with each other: two find it helps, one finds it hurts, one finds it protective under attack. None of them holds capability fixed. A mixed group is not only more diverse, it is usually also better on average — so “diversity helped” and “the mix contained a stronger model” are indistinguishable in all four.

Separately, two papers prove that debate between language-model agents is a martingale on belief in the correct answer — it moves belief around but adds nothing in expectation. Crucially, that proof holds under homogeneous agents. Our design violates that condition on purpose.

The question, stated the way it should appear in the paper Debate among homogeneous agents preserves expected correctness. Does architectural heterogeneity break that — and when an adversary is present, does it break it in the direction of truth? This is not a hunch. It is a well-posed question with a published theorem as its null hypothesis, and nobody has answered it: every paper that studies heterogeneity studies it cooperatively, and every paper that studies adversaries uses identical agents.

## What we would build

- A simulation framework in which 20 language-model agents, connected in a network, discuss a factual claim over several rounds.

- Two of them are seeded with a plausible-sounding falsehood and instructed to argue for it.

- We track each agent’s belief state every round and measure how far, how fast, and how permanently the falsehood spreads.

- We repeat this across five levels of population diversity, all matched to the same average single-agent accuracy — which is the control nobody else has.

# 2.  Where the field actually is

This matters more than it might seem, so it is worth being blunt: a substantial part of the original project idea turned out to be already published. We found this out before writing any code, which is the entire reason for the process described in Section 7.

## Already published — we claim none of it

| Result | Published by |
| --- | --- |
| Injected misinformation spreads through communities of communicating LLM agents | Ju et al. (Science China Inf. Sci., 2026); Becker et al. (2026) |
| Network topology modulates how far errors spread | NetSafe (Findings of ACL 2025); Shen et al. (EMNLP 2025); Li et al. (2024) |
| Heterogeneity helps under adversarial peers — at a single revision step | Nilayam et al. (ServiceNow, June 2026) |
| Debate is a martingale on correct-answer belief | Choi, Zhu & Li (2025) |
| Diversity and confidence improve debate outcomes | Zhu et al. (Cambridge, Jan 2026) |

## What is still open, and why

Two gaps survived a deliberately adversarial search, and both are structural rather than accidental:

The capability confound. All four heterogeneity results vary diversity and competence together. One paper’s “homogeneous” arm is GPT-5 + GPT-4.1 + GPT-3.5-turbo — that is not a matched control, it is a weakened one. Holding measured accuracy fixed changes what the claim means, and it is expensive for others to retrofit.

One step is not a cascade. The closest paper measures exactly one revision step and says why: “later rounds compound direct peer influence with path dependence.” A second group independently flags capitulation cascades and designs around them. Two independent groups have named multi-round cascade dynamics as the thing they were avoiding. That is the open problem.

The honest framing, which we should keep We are not first to the idea that diversity might protect. We are first to test it with capability controlled, over multiple rounds, under an adversary. If the answer is no, that is also publishable — and we have committed in writing, before collecting any data, to reporting it as no.

# 3.  How the experiment works

## The setup

| Element | Design |
| --- | --- |
| Agents | 20 per run, each an independent language-model instance |
| Network | Agents see messages only from their graph neighbours; complete, random and small-world structures compared |
| Task | A factual claim with unambiguous ground truth (e.g. “the adult skeleton has 206 bones”) |
| Attack | 2 agents seeded with a plausible falsehood and a persuasive persona |
| Rounds | Set by how long cascades take to develop — measured, not guessed |
| Measurement | Every agent probed each round on both the true and the false claim, separately |

## The diversity ladder — the core design object

Every prior study compares one homogeneous group against one mixed group. That cannot distinguish “architectural diversity protects” from “any decorrelation protects”. Five levels can:

| Level | Composition | Source of decorrelation |
| --- | --- | --- |
| D0 | 20 identical agents, temperature 0 | None (baseline) |
| D1 | 20 identical agents, sampling temperature > 0 | Sampling noise only |
| D2 | 20 identical agents, several distinct personas | Prompting |
| D3 | 4 different model families, accuracy-matched to D0 | Pre-training / architecture |
| D4 | Families × personas | Both |

Either outcome is a result. If D1 and D2 protect as well as D3, diversity is cheap — you do not need four model families, just varied sampling. That is more useful to a practitioner and is currently unknown. If only D3 and D4 protect, architectural diversity is doing something prompting cannot. Three of the five levels use a single served model, so most of the ladder costs almost nothing extra to run.

## Capability matching — the methodological core

- Every candidate model answers the full validated fact suite alone, many times. This gives a measured accuracy per model.

- Cohorts are then built so that every level of the ladder has the same average single-agent accuracy.

- Accuracy is also entered as a statistical covariate — matched by design and adjusted for, because either alone is contestable.

- A second, less obvious benefit: diversity statistics are known to be nearly collinear with mean accuracy. Holding accuracy fixed breaks that collinearity by construction, which is what makes the diversity measure interpretable at all.

## What we measure

Agents in this size class do not shade their beliefs gradually — published evidence and our own design review say they flip. So the outcome is a discrete state, and the statistics are survival analysis:

| Outcome | Meaning |
| --- | --- |
| Capitulation hazard | Rate at which agents holding the truth switch to the falsehood — the primary outcome |
| Truth-acquisition hazard | Rate at which agents who were wrong become right — the counterpart that stops us confusing “resists lies” with “transmits nothing” |
| Recovery rate | Do agents that fall come back? No classical contagion model predicts this |
| Cascade size, onset, velocity | How far, how soon, how fast — the dynamics that prior work set aside |
| State assortativity | Do agents that capitulate cluster together in the network? (Echo chambers) |

# 4.  Where the project stands today

Everything below has been done without any GPU compute. That was deliberate — see Section 7.

| Component | Status | Notes |
| --- | --- | --- |
| Research method, SOPs, decision/risk registers | Done | 9 procedures, 4 append-only registers |
| Prior-art review and positioning | Done | ~12 papers; 4 mis-citations traced and corrected |
| Experimental design (hypotheses, ladder, controls) | Done | AMD-0001 |
| Metrics and statistical analysis plan | Done | AMD-0002 |
| Analysis pipeline (code) | Done | 25 tests passing |
| Pipeline validation against planted effects | Done | EXP-A01 |
| Power analysis → sample size | Done | EXP-A02 |
| Fact suite | Draft | 31 candidates, awaiting validation |
| Model pool selection | Done | 4 families, all Apache-2.0 |
| Release / dual-use position | Done | DR-0011 |
| Simulation engine | Next | Buildable without GPU using a stub agent |
| Pilot experiment (EXP-000) | Blocked on compute | Needs ~$5 of GPU time |
| Main experiment | Not started | Gated on the pilot |

Design-freeze gate: 10 of 18 evidence requirements closed. Of the 8 remaining, 5 need GPU time — and all 5 are satisfied by a single pilot run estimated at four to six GPU-hours.

# 5.  Two results we already have

These are not about the research question — they are about whether our instruments work. Both cost nothing and both changed the design.

## EXP-A01: the analysis pipeline does not invent findings

Before touching real data we generated synthetic data with a known planted effect and checked that the pipeline recovers it — and, more importantly, that it finds nothing when nothing is there.

| Check | Result | Verdict |
| --- | --- | --- |
| Recovers a planted effect | Bias under 3% | Pass |
| Standard errors correctly sized | SE / observed SD = 0.94–1.07 | Pass |
| False positives on null data | 6.0–6.7% vs nominal 5% | Pass |
| Same null data, naive standard errors | 12.0% | Would have failed |

That last row is the point. Agents inside one run are not independent — they share a network, a fact and a seed, and they talk to each other. Treating them as independent doubles the false-positive rate. Roughly one in five of our “significant” findings would have been noise, and no amount of care later would have caught it.

## EXP-A02: the sample size, and a smallest effect we can actually detect

We simulated statistical power using the same estimator that will analyse the real data. Three findings changed the design:

- The effect size we originally proposed as “worth detecting” was unreachable. It would have needed roughly 600 runs. We revised it to a one-third reduction in capitulation hazard, which needs about 140 — and is below the effect sizes reported in comparable published work.

- More rounds buy almost no statistical power. Going from 3 rounds to 10 multiplies observations by 2.4 but moves power from 0.92 to 0.97, because extra rounds add correlated observations within the same runs. So the number of rounds is set purely by the science — how long cascades take — and not by statistics.

- Runs matter more than agents, which matter more than rounds. When compute is tight, cut agents and rounds before cutting runs. Design settled at 200 runs, 20 agents.

# 6.  What is hard — stated plainly

You should know these before agreeing to anything.

| Risk | Reality | How we handle it |
| --- | --- | --- |
| We get scooped | An established lab (Göttingen) publicly named both of our axes as their next step in June 2026 | Compete on the capability-matched, multi-round version they cannot cheaply retrofit; post the preprint early; re-sweep the literature before submission |
| No GPU funding | The original $280 credit pool expired. Currently unfunded | All work so far is GPU-free. The pilot fits in a recurring free monthly credit. Institutional compute is the main ask (Section 10) |
| The hypothesis is wrong | Genuinely possible — one paper suggests heterogeneity does not help in accuracy-oriented settings | We committed in writing, before any data, to publishing a null as a null. The framework, benchmark and measurement protocol are contributions either way |
| The measurement does not work | The whole study rests on being able to read an agent’s belief reliably | Stop-and-redesign criteria written in advance; the pilot tests them before anything else is run |
| Timeline slips | The original 8-week plan did not survive contact with reality | We hold the quality gate and let the date move. The arXiv preprint is deadline-independent |

# 7.  How we would work

The repository is not just code — it is the lab notebook. Four things are worth knowing because they will shape day-to-day work:

- Append-only registers. Decisions, open questions and risks each have a numbered register. We never edit history; we supersede it. Anyone can see why the project looks the way it does.

- Nothing enters the paper without provenance. Every number points to the script that produced it. Every citation must be verified against the actual source — we have already caught four mis-citations, two of them from peer-reviewed bibliographies.

- Preregistration. Hypotheses, metrics and analyses are frozen and hashed before the main experiment runs. Anything not preregistered is labelled exploratory in the paper. This is the single strongest defence against accidentally fooling ourselves.

- Phase gates. We do not advance until the evidence for the current gate exists. Under time pressure we cut scope, never method.

None of this is bureaucracy for its own sake. It is what makes a first paper survive a hostile reviewer — and, frankly, a public record of this quality is itself a strong signal to admissions committees and to any professor deciding whether to back us.

# 8.  Proposed division of work

The principle Not an even split by type of work — a fair split by opportunity. Both of us should end this project with code we own, results we own, and a section of the paper we wrote. Nobody should be doing only literature review, and nobody should be doing only engineering. Abhijit leans engineering and inference; [Co-researcher] leans experimental design, validation and the institutional track — but both of us hold real technical ownership and both of us hold real research ownership.

## 8.1  Abhijit — Engineering & Inference Lead

| Area | Deliverable |
| --- | --- |
| Simulation engine | Agent orchestration, memory operator, message scheduling, structured logging |
| Inference infrastructure | Self-hosted model serving (vLLM), deployment, batching, cost control |
| Belief instrument | Probe implementation and the validation runs behind it |
| Survival analysis | Primary statistical models (built and validated already) |
| Theory | The martingale framing and hypothesis formalisation |
| Preregistration | Primary author (co-signed) |
| Paper | Method and Results sections |

## 8.2  Divyesh — Experimental & Validation Lead

Three of these are genuine technical ownership with code and a results section attached, not support work.

| Area | Deliverable |
| --- | --- |
| Network topology module | Graph builders, per-receiver message-budget sampling, density matching. Self-contained, testable, and it is what makes the topology comparison valid at all |
| Classical contagion baseline | Implement SIR / threshold / bounded-confidence models on the same graphs and show where LLM dynamics diverge. No GPU needed. This is very likely its own results section and it directly substantiates the paper’s central claim about why LLM societies need studying separately |
| Cascade & network analysis | Run-level cascade outcomes and echo-chamber (assortativity) analysis — the complement to Abhijit’s survival models |
| Systematic prior-art coverage | Forward and backward citation traversal, OpenReview reviews, AAMAS/WWW/ICWSM. Currently a blocking gate requirement — institutional library access helps here |
| Fact suite validation | Independently verify ground truth for all 31 candidate items; design the paraphrase probe templates |
| Human validation study | Design the annotation protocol, run the ethics route, manage the platform, compute inter-annotator agreement |
| Paper | Related Work and Limitations sections |

## 8.3  Shared

- Weekly written check-in in the research log — 15 minutes, non-negotiable, it is what keeps the registers honest.

- Both sign the preregistration before it is frozen.

- Claims audit before submission: every claim in the abstract and introduction traced to a figure or a test. Two hours, highest-return two hours in the project.

- Either of us can block a phase gate on a quality concern, without needing to justify it as anything more than a concern.

## 8.4  Why this split

- It plays to structural advantage. Being inside an institute unlocks things that are simply unavailable otherwise — an advisor, compute grants, an ethics route, paywalled literature, and a credible path into a workshop. That is not admin; it is the difference between this being a hobby project and a publishable one.

- It is not coding versus reading. The topology module and the contagion baseline are real engineering. The martingale framing and the preregistration are real research. Both of us do both.

- Everything has exactly one owner. Shared responsibility for a deliverable reliably means nobody does it.

- It is negotiable. This is a proposal, not an allocation. If you want the survival analysis or the engine, say so — the point is that we both grow, and I would rather rebalance now than discover in week five that you are bored.

# 9.  What we would need from the institute

Ranked by how much it unblocks.

| # | Ask | Why it matters |
| --- | --- | --- |
| 1 | A faculty advisor willing to back the project | Unlocks almost everything else: compute, ethics, and a credible affiliation on the submission. Even light-touch supervision changes how a workshop reads the paper |
| 2 | GPU access — institute cluster or a grant | The single hard blocker. We need roughly 4–6 GPU-hours for the pilot and perhaps 50–150 for the full study, on 7–9B models. This is a small ask by cluster standards |
| 3 | Ethics / IRB determination for the annotation study | We plan to pay human annotators. This cannot be obtained retroactively, and some venues ask |
| 4 | Library access | Several relevant papers sit behind paywalls |
| 5 | Advice on venue and timing | Which workshop, which deadline, and whether an advisor would co-author |

Worth emphasising when you approach a professor: this is not a request to supervise from scratch. The design is done, the analysis pipeline is built and validated, the literature position is written, and the whole thing is publicly auditable. The ask is compute, an ethics route, and guidance — not rescue.

# 10.  Agenda — what to decide today

If we get through nothing else, get through this.

| # | Decision | Notes |
| --- | --- | --- |
| 1 | Are you in, and at what intensity? | Realistic hours per week matters more than enthusiasm |
| 2 | Authorship order and contribution roles | Agreed in writing now, before any results exist. This is standard practice and it prevents the single most common way collaborations break |
| 3 | Does the work split in Section 8 look fair to you? | Say now if you want a different piece |
| 4 | Advisor — who, and who approaches them? | Ideally within two weeks |
| 5 | Compute route | Institute cluster, grant, or self-funded pilot first |
| 6 | Whether an advisor joins as an author | Affects venue strategy |
| 7 | Weekly cadence | Proposal: one 30-minute call, plus written log entries |
| 8 | Anything in Section 6 that worries you | Better raised now than in week six |

# 11.  Indicative sequence

Deliberately not dated — we hold the quality gate, not a calendar. Rough ordering:

| Stage | Work | Gated on |
| --- | --- | --- |
| Now | Simulation engine (stub agents, no GPU); topology module; prior-art coverage; fact-suite verification | Nothing — all GPU-free |
| Next | Pilot: model accuracy, fact validation, belief-instrument checks, cost measurement | A few GPU-hours |
| Then | Freeze and hash the preregistration | Pilot results + power re-run |
| Then | Main experiment | Compute |
| Then | Analysis, human validation, dashboard | Data |
| Finally | Paper, arXiv, workshop submission | Results |

# Appendix — key papers

Full notes, threat ratings and the corrected citations are in the repository under docs/02-literature/.

| Paper | arXiv / venue | Why it matters to us |
| --- | --- | --- |
| Nilayam et al., Heterogeneous LLM Debate Under Adversarial Peers | 2606.19826 | Closest result. Heterogeneity protects under attack — but at one revision step only |
| Sela, Preserving Disagreement | 2604.26561 | Scale-matched architectural heterogeneity with real effect sizes. Also the source of the finding that small models flip rather than shade |
| Choi, Zhu & Li, Debate or Vote | 2508.17536 | Proves debate is a martingale on correct-answer belief. Gives our control arm a theoretical prediction |
| Zhu et al., Demystifying Multi-Agent Debate | 2601.19921 | States the martingale holds under homogeneous agents — which is the hook our whole framing hangs on |
| Wan et al., The Deliberative Illusion | 2606.03032 | Mixed-family groups retain more facts, but capability-confounded |
| Han et al., Conformity Dynamics | 2601.05606 | Varies topology and heterogeneity together; concludes the strongest model dominates |
| Becker et al., Misinformation Propagation in Benign MAS | 2606.16710 | Closest on the phenomenon; named our two axes as their future work |
| Shen et al., Information Propagation Effects of Communication Topologies | EMNLP 2025 | Sparse networks suppress true information too — why we measure both directions |
| Chuang et al., Simulating Opinion Dynamics | NAACL 2024 | Validated protocol for measuring agent belief without model internals |

This document reflects the repository as of 8 August 2026. The registers, decision records and experiment reports referenced throughout are public and current.